## Instructions
CRDP Support Effort Estimator
Purpose
Use this workbook to compare monthly and annual incremental support effort for tokenization capability across different application portfolio sizes and rollout assumptions.
The calculation used on the scenario tabs is: Support Effort = Base Complexity x Readiness Multiplier x Criticality Multiplier x Data/Performance Multiplier.
How to use it
1. Review or edit the multiplier tables on the Assumptions and Conservative_Assumptions tabs.
2. On each Scenario tab, adjust application counts and dropdown-style labels directly in the cells.
3. Base complexity hours are sample midpoint assumptions from the estimating guide.
4. The 250-app scenario is intentionally broad and may overstate scope before the assessment tool narrows true change owners.
5. The 100-app and 50-app scenarios model what support can look like after assessment-based scope reduction.
6. Portfolio_Summary compares baseline and conservative assumptions side by side.
7. Role_Breakdown allocates monthly hours across roles such as DevOps, DBA, Thales admin, and application support.
8. Visual_Summary provides chart-like bars using formulas so the workbook stays self-contained.
Scenario design intent
Scenario_250 = broad pre-assessment estate view
Scenario_100 = likely in-scope portfolio after ownership analysis
Scenario_50 = focused rollout wave or narrowed true-change-owner population
FTE note
Monthly FTE is calculated using 160 hours per month as a planning assumption.

## Assumptions
Assumption Tables
Base Complexity | Hours / App / Month | Readiness | Multiplier | Criticality | Multiplier | Data / Performance | Multiplier
Low | 3 | High | 0.95 | BusinessHours | 1 | Low | 1
Medium | 9.5 | Medium | 1.1 | Near24x7 | 1.3 | Moderate | 1.2
High | 24 | Low | 1.5 | HighlyCritical | 1.6 | High | 1.5
Notes
Low / Medium / High base complexity hours are midpoint planning assumptions derived from the estimating guide.
You can change any multiplier in this sheet and all baseline scenario totals will recalculate when the workbook is opened in Excel.
For front-end reference-only populations, the assessment tool often reduces the true support scope substantially.

## Conservative_Assumptions
Conservative Assumption Tables
Base Complexity | Hours / App / Month | Readiness | Multiplier | Criticality | Multiplier | Data / Performance | Multiplier
Low | 3 | High | 0.9 | BusinessHours | 1 | Low | 1
Medium | 9.5 | Medium | 1 | Near24x7 | 1.15 | Moderate | 1.1
High | 24 | Low | 1.25 | HighlyCritical | 1.35 | High | 1.25
Notes
This tab models a lighter steady-state support assumption after reusable wrappers, good automation, and stable platform operations are in place.
These multipliers are useful for customer conversations where Thales policy administration and application break-fix are expected to remain low after onboarding.
Use this set when you want to show an efficiency-oriented operating model alongside the baseline view.

## Portfolio_Summary
Portfolio Scenario Summary
These totals roll up the scenario tabs and show how scope reduction changes support assumptions.
Scenario | Applications | Baseline Monthly Hours | Baseline Annual Hours | Baseline Monthly FTE | Conservative Monthly Hours | Conservative Annual Hours | Conservative Monthly FTE | Interpretation
250 apps | [7 empty] | Broad pre-assessment estate view. Likely overstates true change-owner scope.
100 apps | [7 empty] | Post-assessment view where front-end-only references and low-impact apps are reduced.
50 apps | [7 empty] | Focused rollout wave or narrowed set of true back-end/data-access owners.

## Scenario_250
250 Application Support Effort Scenario
Sample assumptions. Edit counts or multiplier labels as needed.
Use Case | Application Count | Complexity | Base Complexity Hours / App / Month | Readiness | Readiness Multiplier | Criticality | Criticality Multiplier | Data / Performance | Data / Performance Multiplier | Adjusted Monthly Hours / App | Total Monthly Hours | Notes
Front-end reference / proxy review | 150 | Low |  | Medium |  | BusinessHours |  | Low |  |  |  | Many may only reference sensitive fields; assessment often removes most from true change scope.
Back-end API owners | 30 | Medium |  | Medium |  | Near24x7 |  | Moderate |  |  |  | Primary REST and service owners after assessment.
JDBC candidate applications | 20 | Low |  | High |  | BusinessHours |  | Moderate |  |  |  | Lower incremental support if driver-based coverage is feasible.
Kafka producers / consumers | 10 | High |  | Medium |  | HighlyCritical |  | High |  |  |  | Message-contract, replay, and reveal/protect troubleshooting sensitivity.
Mainframe / WebSphere / Oracle | 10 | High |  | Low |  | HighlyCritical |  | High |  |  |  | Cross-platform support and contractor-readiness risk.
Databricks reveal / batch | 20 | Medium |  | Medium |  | BusinessHours |  | High |  |  |  | Batch windows and downstream analytics dependencies.
Analytics / reveal-heavy | 10 | High |  | Medium |  | Near24x7 |  | High |  |  |  | Large result sets and performance sensitivity.
Total applications
Total monthly hours
Total annual hours
Estimated monthly FTE (160h)

## Scenario_100
100 Application Support Effort Scenario
Sample assumptions. Edit counts or multiplier labels as needed.
Use Case | Application Count | Complexity | Base Complexity Hours / App / Month | Readiness | Readiness Multiplier | Criticality | Criticality Multiplier | Data / Performance | Data / Performance Multiplier | Adjusted Monthly Hours / App | Total Monthly Hours | Notes
Front-end reference / proxy review | 20 | Low |  | Medium |  | BusinessHours |  | Low |  |  |  | Reduced scope after ownership analysis.
Back-end API owners | 25 | Medium |  | Medium |  | Near24x7 |  | Moderate |  |  |  | Likely true REST and business-logic change owners.
JDBC candidate applications | 15 | Low |  | High |  | BusinessHours |  | Moderate |  |  |  | Lower app-support burden if driver strategy is used.
Kafka producers / consumers | 10 | High |  | Medium |  | HighlyCritical |  | High |  |  |  | Shared integration support required.
Mainframe / WebSphere / Oracle | 10 | High |  | Low |  | HighlyCritical |  | High |  |  |  | Older middleware and cross-team coordination risk.
Databricks reveal / batch | 10 | Medium |  | Medium |  | BusinessHours |  | High |  |  |  | Batch and data anomaly support.
Analytics / reveal-heavy | 10 | High |  | Medium |  | Near24x7 |  | High |  |  |  | Reveal-heavy performance review.
Total applications
Total monthly hours
Total annual hours
Estimated monthly FTE (160h)

## Scenario_50
50 Application Support Effort Scenario
Sample assumptions. Edit counts or multiplier labels as needed.
Use Case | Application Count | Complexity | Base Complexity Hours / App / Month | Readiness | Readiness Multiplier | Criticality | Criticality Multiplier | Data / Performance | Data / Performance Multiplier | Adjusted Monthly Hours / App | Total Monthly Hours | Notes
Front-end reference / proxy review | 5 | Low |  | Medium |  | BusinessHours |  | Low |  |  |  | Small residual population after assessment and rollout prioritization.
Back-end API owners | 15 | Medium |  | Medium |  | Near24x7 |  | Moderate |  |  |  | Primary wave of back-end owners.
JDBC candidate applications | 10 | Low |  | High |  | BusinessHours |  | Moderate |  |  |  | Targeted lower-impact rollout group.
Kafka producers / consumers | 5 | High |  | Medium |  | HighlyCritical |  | High |  |  |  | Event-driven use case wave.
Mainframe / WebSphere / Oracle | 5 | High |  | Low |  | HighlyCritical |  | High |  |  |  | High-touch legacy integration subset.
Databricks reveal / batch | 5 | Medium |  | Medium |  | BusinessHours |  | High |  |  |  | Batch-focused rollout slice.
Analytics / reveal-heavy | 5 | High |  | Medium |  | Near24x7 |  | High |  |  |  | Performance-sensitive reveal subset.
Total applications
Total monthly hours
Total annual hours
Estimated monthly FTE (160h)

## Scenario_250_Conservative
250 Application Conservative Support Effort Scenario
Sample assumptions. Edit counts or multiplier labels as needed.
Use Case | Application Count | Complexity | Base Complexity Hours / App / Month | Readiness | Readiness Multiplier | Criticality | Criticality Multiplier | Data / Performance | Data / Performance Multiplier | Adjusted Monthly Hours / App | Total Monthly Hours | Notes
Front-end reference / proxy review | 150 | Low |  | Medium |  | BusinessHours |  | Low |  |  |  | Many may only reference sensitive fields; assessment often removes most from true change scope.
Back-end API owners | 30 | Medium |  | Medium |  | Near24x7 |  | Moderate |  |  |  | Primary REST and service owners after assessment.
JDBC candidate applications | 20 | Low |  | High |  | BusinessHours |  | Moderate |  |  |  | Lower incremental support if driver-based coverage is feasible.
Kafka producers / consumers | 10 | High |  | Medium |  | HighlyCritical |  | High |  |  |  | Message-contract, replay, and reveal/protect troubleshooting sensitivity.
Mainframe / WebSphere / Oracle | 10 | High |  | Low |  | HighlyCritical |  | High |  |  |  | Cross-platform support and contractor-readiness risk.
Databricks reveal / batch | 20 | Medium |  | Medium |  | BusinessHours |  | High |  |  |  | Batch windows and downstream analytics dependencies.
Analytics / reveal-heavy | 10 | High |  | Medium |  | Near24x7 |  | High |  |  |  | Large result sets and performance sensitivity.
Total applications
Total monthly hours
Total annual hours
Estimated monthly FTE (160h)

## Scenario_100_Conservative
100 Application Conservative Support Effort Scenario
Sample assumptions. Edit counts or multiplier labels as needed.
Use Case | Application Count | Complexity | Base Complexity Hours / App / Month | Readiness | Readiness Multiplier | Criticality | Criticality Multiplier | Data / Performance | Data / Performance Multiplier | Adjusted Monthly Hours / App | Total Monthly Hours | Notes
Front-end reference / proxy review | 20 | Low |  | Medium |  | BusinessHours |  | Low |  |  |  | Reduced scope after ownership analysis.
Back-end API owners | 25 | Medium |  | Medium |  | Near24x7 |  | Moderate |  |  |  | Likely true REST and business-logic change owners.
JDBC candidate applications | 15 | Low |  | High |  | BusinessHours |  | Moderate |  |  |  | Lower app-support burden if driver strategy is used.
Kafka producers / consumers | 10 | High |  | Medium |  | HighlyCritical |  | High |  |  |  | Shared integration support required.
Mainframe / WebSphere / Oracle | 10 | High |  | Low |  | HighlyCritical |  | High |  |  |  | Older middleware and cross-team coordination risk.
Databricks reveal / batch | 10 | Medium |  | Medium |  | BusinessHours |  | High |  |  |  | Batch and data anomaly support.
Analytics / reveal-heavy | 10 | High |  | Medium |  | Near24x7 |  | High |  |  |  | Reveal-heavy performance review.
Total applications
Total monthly hours
Total annual hours
Estimated monthly FTE (160h)

## Scenario_50_Conservative
50 Application Conservative Support Effort Scenario
Sample assumptions. Edit counts or multiplier labels as needed.
Use Case | Application Count | Complexity | Base Complexity Hours / App / Month | Readiness | Readiness Multiplier | Criticality | Criticality Multiplier | Data / Performance | Data / Performance Multiplier | Adjusted Monthly Hours / App | Total Monthly Hours | Notes
Front-end reference / proxy review | 5 | Low |  | Medium |  | BusinessHours |  | Low |  |  |  | Small residual population after assessment and rollout prioritization.
Back-end API owners | 15 | Medium |  | Medium |  | Near24x7 |  | Moderate |  |  |  | Primary wave of back-end owners.
JDBC candidate applications | 10 | Low |  | High |  | BusinessHours |  | Moderate |  |  |  | Targeted lower-impact rollout group.
Kafka producers / consumers | 5 | High |  | Medium |  | HighlyCritical |  | High |  |  |  | Event-driven use case wave.
Mainframe / WebSphere / Oracle | 5 | High |  | Low |  | HighlyCritical |  | High |  |  |  | High-touch legacy integration subset.
Databricks reveal / batch | 5 | Medium |  | Medium |  | BusinessHours |  | High |  |  |  | Batch-focused rollout slice.
Analytics / reveal-heavy | 5 | High |  | Medium |  | Near24x7 |  | High |  |  |  | Performance-sensitive reveal subset.
Total applications
Total monthly hours
Total annual hours
Estimated monthly FTE (160h)

## Role_Breakdown
Role-Based Monthly Effort Allocation
Percentages are editable planning allocations applied to the baseline monthly scenario totals.
Role | Allocation % | 250 Apps Monthly Hours | 100 Apps Monthly Hours | 50 Apps Monthly Hours | Role Description
Application developers / integration engineers | 0.18 |  |  |  | Back-end change owners, wrappers, break-fix, vendor coordination
DevOps / SRE | 0.27 |  |  |  | AKS operations, observability, certificates, scaling, platform support
Thales security administration | 0.1 |  |  |  | Policies, user sets, audit review, key lifecycle oversight
DBA / data engineering | 0.15 |  |  |  | Protected tables, data-load planning, schema validation, SQL review
Cloud architects / platform engineering | 0.08 |  |  |  | Cluster topology, network design, workload placement guidance
Performance / capacity engineering | 0.1 |  |  |  | Prometheus review, reveal-heavy tuning, autoscaling thresholds
Service management / release coordination | 0.07 |  |  |  | Incidents, releases, change windows, escalation tracking
Databricks / analytics specialists | 0.05 |  |  |  | Batch UDFs, analytics reveal flows, downstream data consumers
Allocation total

## Visual_Summary
Visual Summary
Formula-based bars provide a simple chart-like view without requiring external libraries.
Scenario | Baseline Monthly Hours | Baseline Bar | Conservative Monthly Hours | Conservative Bar | Baseline FTE | Conservative FTE
250 apps
100 apps
50 apps